## Notes
Contest Procedures & Checklist for Speech Contests in District 50
Updated 2025 January 8
CONTEST CHECKLIST
Please read through this page before continuing to the checklist. This checklist has been designed to support area contests. It can be used as a reference for club contests. For division contests, consider including items marked “optional;” also, division contests have more judges. Please also review the Speech Contest Rulebook provided by Toastmasters International available here
https://www.toastmasters.org/Resources/2024-2025 Speech Contest Rulebook
Contact information provided should be used solely for the purpose of conducting this contest.
Please make sure to get day and evening contact information for all participants. The contest chair and Area Director cannot be held responsible for or to anyone who provides limited-access phone numbers/emails.
The "Cover" tab should be completed with all the contest information as soon as it is available. Once the contest date is entered, the rest of the checklist will automatically indicate suggested due dates for the various tasks. TABS below indicate order of completion, left to right.
This workbook has been protected to ensure version control. Any requests for changes or suggestions should be submitted to qualitycontest@d50tm.org

## Cover
Contest Procedures & Checklist for Speech Contests in District 50
District 50 Contest Checklist
COVER
|  |  | Checklist Date: |  | 2025-08-24
XXXXXXXXXXX
AREA/DIVISION
| Divison Director, Phone & Email: |  |  | Texts OK? _
| Contest Chair, Phone & Email: |  |  | Texts OK? _
| Contest Master, Phone & Email: |  |  | Texts OK? _
| Contest Date & Start Time: | 2025-02-22 10:00
Note: Due Dates will auto-populate to other worksheets.
Area Contacts
Area Name | Area Director | Email | Phone Number | Texts OK? | Alt. Phone Number

## 6 Weeks Prior
Contest Procedures & Checklist for Speech Contests in District 50
District 50 Contest Checklist
FIRST THINGS FIRST - 6 Weeks Out
Item | Details | Info/Notes |  | Assigned to | Due Date | Date Completed
Select Contest Chair
| If you are not the Contest Chair, hand him/her this checklist and assist as needed on all these items, Especially down to “Contest Master.” | CONTEST CHAIR: (name & edu level) |  | Name: | 2025-01-11 10:00
Contest Date
| Date will already have been assigned. | CONTEST DAY / DATE | 2025-02-22 10:00 | Name: | 2025-01-11 10:00
AM / PM
Chief Judge | Contest Chief Judge will be assigned by District 50 Chief Judge. | CONTEST CHIEF JUDGE: (name & edu level) |  | N/A
If not assigned by 2-3 weeks before your contest, Contact D50 Chief Judge & District leaders and ask!
You should be given the contact information For your assigned Chief Judge.
Start creating a Flyer and send for Approval 4 weeks Prior
| Review the Flyer pdf from the www.d50tm.org Create your flyer and proof it! Keep it clean, fun, easy to print. Include Contact info. | FLYER DONE? |  | Name: | 2025-01-11 10:00
| PROOF IT!! Save as PDF & name the file with your Area Number. | PROOFED? |  | Name: | 2025-01-11 10:00
| Submit version 1 of flyer to qualitycontest@d50tm.org | FLYER SENT FOR APPROVAL? |  | Name: | 2025-01-25 10:00
| WHEN APPROVED, send to other ADs in the Division and to your Division Director. Final approved flyer will be posted to district website by the Quality Contest Chair | FLYER SENT TO ADs / DDs / CJ? |  | Name: | 2025-01-25 10:00
| Also send to all clubs / club officers in your Area. | FLYER SENT TO CLUBS / OFFICERS? |  | Name: | 2025-01-25 10:00

## 4 weeks Prior
Contest Procedures & Checklist for Speech Contests in District 50
District 50 Contest Checklist
AS SOON AS POSSIBLE - 4 Weeks Prior
Item | Details | Info/Notes |  | Assigned to | Due Date | Date Completed
Finalize Your Contest Master
| Check with other Area Directors, past Area / Division Directors and past Contest Winners. Your Contest Master sets the tone for your contest. Do NOT pick a new TM or someone who has never attended a contest. |  |  | Name: | 2025-01-25 10:00
Contest Masters should not be competing, and should not serve at more than two Area Contests per season.
DOWNLOAD CONTEST SCRIPT for you & for your Contest Master. If possible, review together for familiarity.
| Contest Master | Contest Master | Educational Level | Email | Phone Number | Alternate Phone Number
Start Selecting Helpers | Select someone who has performed the role before as your Senior Timer/Ballot Counter/SAA. | SEE CONTEST HELPERS TAB for more INFO and a PLACE to RECORD NAMES |  | Name: | 2025-02-08 10:00

## 2 weeks Prior
Contest Procedures & Checklist for Speech Contests in District 50
District 50 Contest Checklist
Close to Contest - 2 Weeks Prior
Item | Details | Info/Notes | Assigned to | Due | Date Completed
Promote Your Contest
| Share your contest flyer during Club visits (if in person) and promote in the D50 facebook page as well as in WhatsApp group. | COPIES OF FLIERS TO DISTRIBUTE? |  | 2025-02-08 10:00
Verify Area Contestants
| Once Club Contests are done, get names and contact info (phones & email), for contestants and alternates. SEE LAST PAGE for a place to record that information. | SEE CONTESTANT TAB TO RECORD THIS INFO |  | 2025-02-08 10:00
Contact All Contestants, Alternates , Contest Master & Chief Judge To Confirm Attendance
| Congratulate them on their win! Encourage alternates to also plan to attend, just in case the winner can’t make it. | CONTESTANTS CONTACTED? |  | 2025-02-08 10:00
The Contest Chief Judge and Contest Master will be sent seperate emails from the contestants Make sure they know time / place / day of the Contest. Remind them that they’ll need to arrive in time for the Contest Briefing. If there are any changes to the time / place / day, contact them again!
Create Contest Program and send for Approval 1 week before contest | Download Program Template from D50 web site. | FLYER DONE? |  | 2025-02-15 10:00
| PROOF IT!! Save as PDF & name the file with your Area Number. | PROOFED?
| Submit version 1 of flyer to qualitycontest@d50tm.org | PROGRAM SENT FOR APPROVAL?
| WHEN APPROVED, send to other ADs in the Division and to your Division Director. Final approved flyer will be posted to district website by the Quality Contest Chair | PEOGRAM SENT TO ADs / DDs / CJ?
| Also send to all clubs / club officers in your Area. | FLYER SENT TO CLUBS / OFFICERS?
Verify Contestant and Club Eligibility | Club should be in good standing with Toastmasters, with a minimum of 8 paid members | Club Eligible? |  | 2025-02-15 10:00
| Contestant(s) and Alternate Contestant(s) should have paid dues at least until the end of the current Toastmasters term during the time of the contest | Contestant Eligible?
Altenate Contestant Eligible?
Tips for Contest Program Prep
List contestants in alphabetical order by last name, and do NOT list their educational levels.
List educational levels for all helpers.
Anyone (other than contestants) without an educational level should be listed as “TM.”
Verify Club Names for spelling and correctness.

## Week of contest
Contest Procedures & Checklist for Speech Contests in District 50
District 50 Contest Checklist
WEEK OF CONTEST
Item | Details | Info/Notes | Assigned to |  | Due Date | Date Completed
Update Contest Powerpoint Slides
Contact Contest Master, Contest Chief Judge and All Contestants to Confirm Attendance!
| Confirm attendance and remind them to be there in time for the briefing. |  | Name: |  | 2025-02-17 10:00
Hold Contestant Briefing
| Hold a contestant, SAA Briefing and pick speaking order. Follow briefing script from d50tm.org/contests. Use https://www.random.org/lists to pick speaking order. Confirm to your Chief Judge that the contestant briefing has been held and communicate speaking order and contestant names. | Have the Contest Master practice pronouncing Contestant names! | Name: |  | 2025-02-19 10:00
Confirm Your Helpers
| Send the program to all helpers and Chief Judge To make sure they know they’re on there! |  | Name: |  | 2025-02-17 10:00
Sergeant-at-Arms, Ballot Counters, and Timers Need to be reminded to show up for the briefing. (Briefing dates and times below)
Confirm attendance of your Division Director and District Representative (someone from Senior 7)
Confirm that Sr SAA has Contest Zoom link and instructions to start contest
Send Contest Info to all Clubs
| Contact your Club Officers (Presidents/VPEs), provide them with contest info and encourage ALL members to attend! |  |  |  | 2025-02-19 10:00
Finalize Contest Program, if any changes since DRAFT was sent
| Communicate any changes to previously approved program to qualitycontest@d50tm.org |  |  |  | 2025-02-19 10:00
Print Program
| Once the Contest Program is proofed and approved by your Chief Judge, and final, make 15-30 copies. |  | Name: |  | 2025-02-19 10:00
| Print front-to-back and fold - Make sure pages are in the correct order! |  | Name: |  | 2025-02-19 10:00
| Briefing | Date | Time | Zoom Link
Ballot Counter, Timer and Judge Briefing
SAA and Contestant Briefing
Other Briefing ?

## Contest Day
Contest Procedures & Checklist for Speech Contests in District 50
District 50 Contest Checklist
CONTEST DAY
Assemble everything you need and head on out to your location as early as possible!
Don’t hesitate to ask for help, and avoid stress - this should be fun!
Awards will be delivered to the contest by the Division Director, unless other arrangements have been previously made.
Contest Debrief
AT THE END OF YOUR CONTEST: Your District Rep will have a short debriefing at the end of the contest with you, Your Division Director, Your Contest Chair, Contest Master & Contest Chief Judge.
This checklist is a template, choose the items that fit your needs or add them if required.
Here’s your checklist:
Description | Ready? | Point of Contact 1 | Point of Contact 2
Drinks
Water:
Other Beverages (optional):
Ice for drinks (if needed):
Serving Items
Flatware (Knives, forks, spoons …):
Plates:
Cups:
Napkins:
Food
Snacks:
Mid-day lunch (if all day contests):
Warming Trays (if needed):
Contest Essentials
Gavel:
Flag:
Stop watches (or smart phone)(2):
Timing lights and/or Cards (2):
Dignitary List:
Sign-in sheets:
Certificates:
Programs:
Awards:
Contest Optionals
Designated Photographer for winners
Lectern (optional):
Campaign Table (when District Leader candidates are announced):
Signs
Outside directional signs (with stakes):
Hammer or Mallet:
Inside directional signs (with tape):

## Contest Helpers
Contest Procedures & Checklist for Speech Contests in District 50
District 50 Contest Checklist
GET CONTEST HELPERS!
Look for helpers among your clubs and your fellow Area Directors. Get names (correct spelling!) and educational levels of helpers, and contact info. Remind your helpers to show up for the Contest Briefing.
For each role, try to get a backup in case one of your assigned helpers backs out or not able to attend. Contestants cannot be helpers.
You need a Sergeant-at-Arms for each door, and extras for Table Topics & Evaluation Contests to escort contestants. Get extra helpers for set-up, clean-up, and as back-ups.
Note: | Do not assign two people from the same club to the same role (Timers or Ballot Counters)
Helper Role | Name | Educational Level | Club (s) | Email | Phone Number | Alternate Number
Inspiration/Pledge:
Sr. Sergeant-at-Arms
Sergeant-at-Arms
Sergeant-at-Arms (see note above)
Sergeant-at-Arms (see note above)
Experienced Timer #1:
Timer #2 (Not from the same club as Timer#1)
Timer (Backup)
Ballot Counter #1
Ballot Counter #2 (Not from the same club as Ballot Counter #1)
Ballot Counter (Backup)
Cleanup Helper:
(Optional) Cleanup Helper:

## Clubs & Contestants
Contest Procedures & Checklist for Speech Contests in District 50
District 50 Contest Checklist
CLUBS & CONTESTANTS
Area |  | Contact Information
Area # | Contest /Place | Contestant Name & Education Level | Email | Phone Number | Alt. Phone Number | Club
First Place Table Topics/Tall Tales/Evaluation:
Alternat Table Topics/Tall Tales/Evaluation:
First Place Humorous/International:
Alternate Humorous/International:
First Place Table Topics/Tall Tales/Evaluation:
Alternat Table Topics/Tall Tales/Evaluation:
| First Place Humorous/International: | [5 empty] | Yes
| Alternate Humorous/International: | [5 empty] | No
First Place Table Topics/Tall Tales/Evaluation:
Alternat Table Topics/Tall Tales/Evaluation:
First Place Humorous/International:
Alternate Humorous/International:
| First Place Table Topics/Tall Tales/Evaluation: | [5 empty] | Yes
| Alternat Table Topics/Tall Tales/Evaluation: | [5 empty] | No
First Place Humorous/International:
Alternate Humorous/International:
First Place Table Topics/Tall Tales/Evaluation:
Alternat Table Topics/Tall Tales/Evaluation:
First Place Humorous/International:
Alternate Humorous/International: